## Sheet2
| Resource | Resource | Resource
Projects/Tasks |  |  |  | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | Overall guidelines
Screen Import Usability | Asad |  |  | 1 | 1 | 1 |  |  | qa | qa | qa | beta | beta | beta | Code reviews
|  |  |  | 2011-11-14: beta; 2011-11-21: beta; 2011-11-28: beta | Guidelines
Documentation Revamp | Haroon | DevX |  | 1.5 | 1.5 | 1.5 | 1.5 |  | qa | qa | qa | beta | beta | beta | Design/Reqs reviews
Communicate bugs fixed in Q1 and Q2 of 2011 | Haroon | bar: 2011-09-19
|  |  |  | 2011-11-14: beta; 2011-11-21: beta; 2011-11-28: beta | Coding / refactor / lead teams
Performance | Haider |  |  |  |  | 1 | 1 | 1 | qa | qa | qa | beta | beta | beta
|  |  |  | 2011-11-14: beta; 2011-11-21: beta; 2011-11-28: beta | Support
Support | Noman | Usman |  | 2 | 2 | 2 | 2 | 2 | qa | qa | qa | beta | beta | beta | Noman
Usman
Installer Issues | Sami | bar: 2011-09-19 to 2011-09-26
Development
Export support for Drop Setter | Zeeshan |  |  | 1 | 1 | 1 | 0.5 | 0.5 | qa | qa | qa |  |  |  | Haroon
Asad
Usability items package | [14 empty] | Awais
Ability to perform operations on drops right from the plate info tab: copy/paste, optimize, reports. Should be able to multiselect. | Mohsin |  |  | 2011-09-19: 0.8 | Mohsin
Image Management: ability to remove images older than X days (e.g. remove Z slices older than 30 days). | Mohsin |  |  | 2011-09-19: 0.2; 2011-09-26: 1 | Zeeshan
Allow searches (new search) to be done in terms of lapsed days [since dispense]. E.g. find all drops imaged between 5 and 10 days after that was scored with a 10. | Mohsin | [13 empty] | Haider | bar: 2011-10-03 to 2011-10-10
Ensure that we can copy/paste from/into experiment or plate notes. | Mohsin | [13 empty] | Sami
Add logging to RM 2.3 (during beta period) to track user actions. A notification should be sent around every 30 days with the actions latest log file. | Mohsin
Automatic Image Management | Sami | [13 empty] | Vacations | bar: 2011-10-03
RM Web
Ability to do window leveling (some form, needs to be defined) | Awais | bar: 2011-09-19
Add a scale bar | Awais | bar: 2011-09-26 to 2011-10-03
FRAP & SONICC Enhancements and suppport | Zeeshan |  |  | 2011-10-10: 0.5; 2011-10-17: 0.5
Application Domain Support | Haider | Haroon |  | 2011-09-19: 1.2; 2011-09-26: 1.2
QA | Waqas | Hamid | Harris | 3 | 3 | 3 | 3 |  | 3 | 3 | 3

## 2.4
Projects/Tasks | Resource | 2011-09-19 | 2011-09-26 | 2011-10-03 | 2011-10-10 | 2011-10-17 | 2011-10-24 | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28
week # |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
[7 empty] | QA | QA | beta | beta | beta | beta
Screen Import Usability | Asad | 2011-09-19: 3; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 2
Documentation Revamp | Haroon | 2011-09-26: 4; 2011-10-03: 4; 2011-10-10: 4; 2011-10-17: 4
Communicate bugs fixed in Q1 and Q2 of 2011 | Haroon | 2011-09-19: 4
Product and project management | Haroon | bar: 2011-09-19 to 2011-10-17
Performance | Haider | 2011-09-26: 3; 2011-10-03: 3; 2011-10-10: 5; 2011-10-17: 5
Application Domain Support | Haider | 2011-09-19: 5; 2011-09-26: 2; 2011-10-03: 2
Installer Issues/Enhancement | Sami | 2011-09-19: 5; 2011-09-26: 5
Automatic Image Management | Sami | 2011-10-03: 5
Export support for Drop Setter | Zeeshan | 2011-09-19: 5; 2011-09-26: 4.5; 2011-10-03: 4; 2011-10-10: 3; 2011-10-17: 2
FRAP & SONICC Enhancements and suppport | Zeeshan | 2011-09-26: 0.5; 2011-10-03: 1; 2011-10-10: 2; 2011-10-17: 3
RM Web
Ability to do window leveling (some form, needs to be defined) | Awais | 2011-09-26: 5; 2011-10-03: 5
Add a scale bar | Awais | 2011-09-19: 5
Add logging to RM 2.3 (during beta period) to track user actions. A notification should be sent around every 30 days with the actions latest log file. | Awais | 2011-10-10: 5
Usability items package
Ability to perform operations on drops right from the plate info tab: copy/paste, optimize, reports. Should be able to multiselect. | Mohsin | 2011-09-19: 2
Image Management: ability to remove images older than X days (e.g. remove Z slices older than 30 days). | Mohsin | 2011-09-19: 3; 2011-09-26: 5; 2011-10-03: 2
Allow searches (new search) to be done in terms of lapsed days [since dispense]. E.g. find all drops imaged between 5 and 10 days after that was scored with a 10. | Mohsin | 2011-10-03: 3; 2011-10-10: 5; 2011-10-17: 2
Ensure that we can copy/paste from/into experiment or plate notes. | Mohsin
Support | Noman | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 5
| Usman | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 5
Haroon |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 5
Noman |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 5
Haider |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 5
Zeeshan |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 5
Awais |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 0
Usman |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 5
Mohsin |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 5; 2011-10-17: 2
Asad |  | 2011-09-19: 3; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 2; 2011-10-17: 0
Sami |  | 2011-09-19: 5; 2011-09-26: 5; 2011-10-03: 5; 2011-10-10: 0; 2011-10-17: 0

## GRAVITY & DRAG
G |  | -9.82 | [5 empty] | dt = t1 - t0
r (air density @ 20c) |  | 3 | 1.225 |  |  |  |  | v = u + at
C (drag coeff) |  | 0.47 | http://en.wikipedia.org/wiki/Drag_coefficient |  |  |  |  | s = ut + 1/2 at ^ 2
A (ref area) |  | 0.0001 | [5 empty] | dist = d0 + s
f (kg) |  | 1 | [5 empty] | fd = 0.5 r v^2 AC |  | http://en.wikipedia.org/wiki/Drag_equation
m=f/a |  | -0.10183 | [5 empty] | f = ma
|  |  | No Drag |  |  | Drag
[8 empty] | f = ma -fd | a=f/m
t | dt |  | v | s | dist | v | fd | f net | a | s | dist* |  |  | v | fd | f net | a | s
0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | -9.82 | 0 | 0 |  | 0.5 | 0 | 0 | 1 | -9.82 | -1.2275
0.5 | 0.5 |  | -4.91 | -1.2275 | -1.2275 | 0 | 0 | 1 | -9.82 | -1.2275 | -1.2275 | -3.7952e-08 | 0.5 | 0 | 0.0016996 | 0.9983 | -9.8033 | -1.2254
1 | 0.5 |  | -9.82 | -3.6825 | -4.91 | -4.91 | 0.0016996 | 0.9983 | -9.8033 | -1.2254 | -2.4529 | -1.1367e-07 | 0.5 | -4.91 | 0.0067869 | 0.99321 | -9.7534 | -3.6742
1.5 | 0.5 |  | -14.73 | -6.1375 | -11.0475 | -9.8117 | 0.0067869 | 0.99321 | -9.7534 | -3.6742 | -6.1271 | -1.8861e-07 | 0.5 | -9.8117 | 0.01521 | 0.98479 | -9.6706 | -6.1147
2 | 0.5 |  | -19.64 | -8.5925 | -19.64 | -14.6883 | 0.01521 | 0.98479 | -9.6706 | -6.1147 | -12.2417 | -2.6204e-07 | 0.5 | -14.6883 | 0.026873 | 0.97313 | -9.5561 | -8.5387
2.5 | 0.5 |  | -24.55 | -11.0475 | -30.6875 | -19.5236 | 0.026873 | 0.97313 | -9.5561 | -8.5387 | -20.7804 | -3.3321e-07 | 0.5 | -19.5236 | 0.041635 | 0.95836 | -9.4111 | -10.9382
3 | 0.5 |  | -29.46 | -13.5025 | -44.19 | -24.3017 | 0.041635 | 0.95836 | -9.4111 | -10.9382 | -31.7186 | -4.0146e-07 | 0.5 | -24.3017 | 0.05932 | 0.94068 | -9.2375 | -13.3055
3.5 | 0.5 |  | -34.37 | -15.9575 | -60.1475 | -29.0073 | 0.05932 | 0.94068 | -9.2375 | -13.3055 | -45.0242 | -4.6614e-07 | 0.5 | -29.0073 | 0.079715 | 0.92029 | -9.0372 | -15.6333
4 | 0.5 |  | -39.28 | -18.4125 | -78.56 | -33.626 | 0.079715 | 0.92029 | -9.0372 | -15.6333 | -60.6575 | -5.2671e-07 | 0.5 | -33.626 | 0.10258 | 0.89742 | -8.8127 | -17.9146
4.5 | 0.5 |  | -44.19 | -20.8675 | -99.4275 | -38.1446 | 0.10258 | 0.89742 | -8.8127 | -17.9146 | -78.5721 | -5.8268e-07 | 0.5 | -38.1446 | 0.12765 | 0.87235 | -8.5665 | -20.1431
5 | 0.5 |  | -49.1 | -23.3225 | -122.75 | -42.551 | 0.12765 | 0.87235 | -8.5665 | -20.1431 | -98.7152 | -6.3368e-07 | 0.5 | -42.551 | 0.15464 | 0.84536 | -8.3015 | -22.3132
5.5 | 0.5 |  | -54.01 | -25.7775 | -148.5275 | -46.8342 | 0.15464 | 0.84536 | -8.3015 | -22.3132 | -121.0283 | -6.794e-07 | 0.5 | -46.8342 | 0.18326 | 0.81674 | -8.0204 | -24.4196
6 | 0.5 |  | -58.92 | -28.2325 | -176.76 | -50.9849 | 0.18326 | 0.81674 | -8.0204 | -24.4197 | -145.448 | -7.1964e-07 | 0.5 | -50.9849 | 0.21322 | 0.78678 | -7.7261 | -26.4582
6.5 | 0.5 |  | -63.83 | -30.6875 | -207.4475 | -54.9951 | 0.21322 | 0.78678 | -7.7261 | -26.4582 | -171.9062 | -7.5429e-07 | 0.5 | -54.9951 | 0.24423 | 0.75577 | -7.4216 | -28.4253
7 | 0.5 |  | -68.74 | -33.1425 | -240.59 | -58.8582 | 0.24423 | 0.75577 | -7.4216 | -28.4253 | -200.3315 | -7.8333e-07 | 0.5 | -58.8582 | 0.276 | 0.724 | -7.1097 | -30.3178
7.5 | 0.5 |  | -73.65 | -35.5975 | -276.1875 | -62.569 | 0.276 | 0.724 | -7.1097 | -30.3178 | -230.6493 | -8.068e-07 | 0.5 | -62.569 | 0.30825 | 0.69175 | -6.793 | -32.1336
8 | 0.5 |  | -78.56 | -38.0525 | -314.24 | -66.1239 | 0.30825 | 0.69175 | -6.793 | -32.1336 | -262.7829 | -8.2485e-07 | 0.5 | -66.1239 | 0.34073 | 0.65927 | -6.474 | -33.8712
8.5 | 0.5 |  | -83.47 | -40.5075 | -354.7475 | -69.5203 | 0.34073 | 0.65927 | -6.474 | -33.8712 | -296.6541 | -8.3767e-07 | 0.5 | -69.5203 | 0.3732 | 0.6268 | -6.1552 | -35.5296
9 | 0.5 |  | -88.38 | -42.9625 | -397.71 | -72.7573 | 0.3732 | 0.6268 | -6.1552 | -35.5296 | -332.1837 | -8.4551e-07 | 0.5 | -72.7573 | 0.40544 | 0.59456 | -5.8386 | -37.1085
9.5 | 0.5 |  | -93.29 | -45.4175 | -443.1275 | -75.8349 | 0.40544 | 0.59456 | -5.8386 | -37.1085 | -369.2921 | -8.4867e-07 | 0.5 | -75.8349 | 0.43726 | 0.56274 | -5.5261 | -38.6082
10 | 0.5 |  | -98.2 | -47.8725 | -491 | -78.7542 | 0.43726 | 0.56274 | -5.5261 | -38.6082 | -407.9004 | -8.4748e-07 | 0.5 | -78.7542 | 0.46848 | 0.53152 | -5.2196 | -40.0295
10.5 | 0.5 |  | -103.11 | -50.3275 | -541.3275 | -81.5173 | 0.46848 | 0.53152 | -5.2196 | -40.0295 | -447.9299 | -8.4229e-07 | 0.5 | -81.5173 | 0.49895 | 0.50105 | -4.9203 | -41.3737
11 | 0.5 |  | -108.02 | -52.7825 | -594.11 | -84.1271 | 0.49895 | 0.50105 | -4.9203 | -41.3737 | -489.3036 | -8.3348e-07 | 0.5 | -84.1271 | 0.52856 | 0.47144 | -4.6295 | -42.6422
11.5 | 0.5 |  | -112.93 | -55.2375 | -649.3475 | -86.5872 | 0.52856 | 0.47144 | -4.6295 | -42.6422 | -531.9458 | -8.2143e-07 | 0.5 | -86.5872 | 0.5572 | 0.4428 | -4.3483 | -43.8371
12 | 0.5 |  | -117.84 | -57.6925 | -707.04 | -88.9019 | 0.5572 | 0.4428 | -4.3483 | -43.8371 | -575.7829 | -8.0651e-07 | 0.5 | -88.9019 | 0.58479 | 0.41521 | -4.0774 | -44.9606
12.5 | 0.5 |  | -122.75 | -60.1475 | -767.1875 | -91.0761 | 0.58479 | 0.41521 | -4.0774 | -44.9606 | -620.7436 | -7.8911e-07 | 0.5 | -91.0761 | 0.61126 | 0.38874 | -3.8174 | -46.0152
13 | 0.5 |  | -127.66 | -62.6025 | -829.79 | -93.1148 | 0.61126 | 0.38874 | -3.8174 | -46.0152 | -666.7588 | -7.6958e-07 | 0.5 | -93.1148 | 0.63658 | 0.36342 | -3.5688 | -47.0035
13.5 | 0.5 |  | -132.57 | -65.0575 | -894.8475 | -95.0235 | 0.63658 | 0.36342 | -3.5688 | -47.0035 | -713.7623 | -7.4827e-07 | 0.5 | -95.0235 | 0.66071 | 0.33929 | -3.3318 | -47.9282
14 | 0.5 |  | -137.48 | -67.5125 | -962.36 | -96.8079 | 0.66071 | 0.33929 | -3.3318 | -47.9282 | -761.6905 | -7.255e-07 | 0.5 | -96.8079 | 0.68365 | 0.31635 | -3.1066 | -48.7923
14.5 | 0.5 |  | -142.39 | -69.9675 | -1032.3275 | -98.4738 | 0.68365 | 0.31635 | -3.1066 | -48.7923 | -810.4828 | -7.0157e-07 | 0.5 | -98.4738 | 0.70538 | 0.29462 | -2.8931 | -49.5986
15 | 0.5 |  | -147.3 | -72.4225 | -1104.75 | -100.0271 | 0.70538 | 0.29462 | -2.8931 | -49.5986 | -860.0814 | -6.7678e-07 | 0.5 | -100.0271 | 0.72593 | 0.27407 | -2.6913 | -50.35
15.5 | 0.5 |  | -152.21 | -74.8775 | -1179.6275 | -101.4737 | 0.72593 | 0.27407 | -2.6913 | -50.35 | -910.4314 | -6.5136e-07 | 0.5 | -101.4737 | 0.74531 | 0.25469 | -2.501 | -51.0495
16 | 0.5 |  | -157.12 | -77.3325 | -1256.96 | -102.8194 | 0.74531 | 0.25469 | -2.501 | -51.0495 | -961.4808 | -6.2557e-07 | 0.5 | -102.8194 | 0.76355 | 0.23645 | -2.3219 | -51.6999
16.5 | 0.5 |  | -162.03 | -79.7875 | -1336.7475 | -104.0699 | 0.76355 | 0.23645 | -2.3219 | -51.6999 | -1013.1808
accel | 0
t | dt |  | v | s | dist | v | fd | f net | a | s | dist*
0 | 0 |  | 4 | 0 | 0 | 4 | 0.001128 | -0.001128 | 0.011077 | 0 | 0
100 | 100 |  | 4 | 400 | 400 | 5.1077 | 0.0018392 | -0.0018392 | 0.018061 | 490.3068 | 490.3068
200 | 100 |  | 4 | 400 | 800 | 6.9138 | 0.00337 | -0.00337 | 0.033093 | 676.2355 | 1166.5423
300 | 100 |  | 4 | 400 | 1200 | 10.2232 | 0.0073682 | -0.0073682 | 0.072355 | 1053.1596 | 2219.7019
400 | 100 |  | 4 | 400 | 1600 | 17.4587 | 0.021489 | -0.021489 | 0.21102 | 2077.414 | 4297.1158
500 | 100 |  | 4 | 400 | 2000 | 38.5607 | 0.10483 | -0.10483 | 1.0294 | 6892.9295 | 11190.0454
600 | 100 |  | 4 | 400 | 2400 | 141.5019 | 1.4116 | -1.4116 | 13.862 | 73165.9408 | 84355.9862
700 | 100 |  | 4 | 400 | 2800 | 1527.6994 | 164.5375 | -164.5375 | 1615.7584 | 8092942.1813 | 8177298.1674
800 | 100 |  | 4 | 400 | 3200 | 163103.5392 | 1875494.8981 | -1875494.8981 | 18417359.8993 | 92086952266.4285 | 92095129564.596
900 | 100 |  | 4 | 400 | 3600 | 1841899093.469 | 2.3918e+14 | -2.3918e+14 | 2348725554805046 | 1.1744e+19 | 1.1744e+19
1000 | 100 |  | 4 | 400 | 4000 | 2.3487e+17 | 3.8891e+30 | -3.8891e+30 | 3.8191e+31 | 1.9096e+35 | 1.9096e+35
1100 | 100 |  | 4 | 400 | 4400 | 3.8191e+33 | 1.0283e+63 | -1.0283e+63 | 1.0098e+64 | 5.0489e+67 | 5.0489e+67
1200 | 100 |  | 4 | 400 | 4800 | 1.0098e+66 | 7.1887e+127 | -7.1887e+127 | 7.0593e+128 | 3.5297e+132 | 3.5297e+132
1300 | 100 |  | 4 | 400 | 5200 | 7.0593e+130 | 3.5133e+257 | -3.5133e+257 | 3.4501e+258 | 1.725e+262 | 1.725e+262
1400 | 100 |  | 4 | 400 | 5600 | 3.4501e+260 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
1500 | 100 |  | 4 | 400 | 6000 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
1600 | 100 |  | 4 | 400 | 6400 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM!
1700 | 100 |  | 4 | 400 | 6800 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! |  | ---------- dt = 0.0350000001490116
1800 | 100 |  | 4 | 400 | 7200 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! |  | curV = (0, 0.531906795452863, 0)
1900 | 100 |  | 4 | 400 | 7600 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! |  | curAcc = (0, 0, 0)
2000 | 100 |  | 4 | 400 | 8000 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! |  | newv = (0, 0.531906795452863, 0)
2100 | 100 |  | 4 | 400 | 8400 | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! | #NUM! |  | ----------
dragF = 1.81956037113346E-05
t | dt |  | v | s | dist | v | fd | f net | a | s | dist* |  | F = 0.999981804396289
Test | [5 empty] | 0.53191 | [6 empty] | newacc = 9.81982101400133
| 0.035 |  | 0 | 0 | 0 | 0.53191 | 1.9946e-05 | 0.99998 | -9.8198 | 0.012602 | 0.012602 |  | dist = 0.0246313783424007
| 0.014 |  | 0 | 0 | 0 | 0.39443 | 1.0968e-05 | 0.99999 | -9.8199 | 0.0064843 | 0.019086 |  | curV = (0, 0.531906795452863, 0)
newAcc = (0, 9.81982101400133, 0)
---------- dt = 0.0140000004321337
curV = (0, 0.531906795452863, 0)
curAcc = (0, 9.81982101400133, 0)
newv = (0, 0.669384293892357, 0)
----------
dragF = 2.88168448477595E-05
F = 0.999971183155152
newacc = 9.81971671341661
dist = 0.00840902766351777
curV = (0, 0.669384293892357, 0)
newAcc = (0, 9.81971671341661, 0)

## Sheet3
Period | Month | Monthly $ | Year $ | Delta | % increase
Nov-Dec 08 | 2008-12-01 | 10417 | 125004
Jan-Jun 09 | 2009-06-01 | 10417 | 125004 | 0 | 0%
Jun-Dec 09 | 2009-12-01 | 10417 | 125004 | 0 | 0%
Jan-Jun 10 | 2010-06-01 | 10812.5 | 129750 | 4746 | 3.797%
Jul-Dec 10 | 2010-12-01 | 11179.17 | 134150.04 | 4400.04 | 3.391%
Jan-Jun 11 | 2011-01-01 | 11397.6 | 136771.2 | 2621.16 | 1.954%
Jul-Dec 11 | 2011-07-01 | 11735.25 | 140823 | 4051.8 | 2.962% | 143609.76 | 147864.15
1.05